## Sheet1
Team: | 1D |  | Unit: person-days (assuming 2 productive hours per person-day)
User Story ID | User Story | Estimation Round | Member 1 Estimate | Member 2 Estimate | Member 3 Estimate | Member 4 Estimate | Agreed Estimate | Actual Time | Priority | Task | Further information | Additional information
1 | As a proprietor of a travel company I want to see the list of orders that have been made, so I can further work with them. | 1 | 3 | 5 | 8 | … | 5 |  | 1 | Upplýsingar vistast eftir að þær séu stimplaðar inn | Getum sláð inn upplýsingar og fundið þær með SQL
2 | As a world traveler I want to see all the available trips in the country before I commit myself to go there, so I don't book trips similar to what I've already taken. | 1 | 13 | 8 | 5 |  | 13 |  | 3,4
3 | As an elderly invalid I want to make sure the day tour I wish to go on is suitable for a person of my physical capabilities so I won't book something I am unable to handle. | 1 | 8 | 5 | 3 |  | 5 | 2 | 4,5
4 | As a choir and orchestra conductor going on a tour to Iceland I want to be able to order a day tour for my entire choir and orchestra, so we can all go together. | 1 | 13 | 5 | 13 |  | 13 |  | 2 | Valmöguleiki á að panta fyrir fleiri en einn í einu | Tenging á milli bókuninni og gagnagrunnurinn sem sér hvað er mikið í boði - breytingar á milli vistast
5 | As a traveler from distant lands I want to be sure my tour guide speaks Chinese before I order a day tour, so that I will understand what the guide is telling me. | 1 | 5 | 5 | 5 |  | 5 | 2 | 3
6 | As a person with a weak bladder and big appetite I want to know about tours that make stops at nice restaurants or shops on the way, so I can satisfy my needs. | 1 | 2 | 8 | 8 |  | - |  | 4
|  | 2 | 3 | 3 | 3 |  | 3
7 | As a traveler from a tropical country I want to know which sort of clothing is appropriate for my day tour, so that I will come well prepared | 1 | 8 | 8 | 5 |  | 8 | 2 | 4
8 | As a traveler, I wish to be able to book a reservation, so that I can plan ahead of time | 1 | 20 | 3 | 8 |  | - |  | 1 | Taka frá bókun sem vistast | Tenging á milli bókun og gagnagrunns sem vistar tímabundið tíma og gefur valmöguleika á að færa þetta yfir á fasta pöntun eða hætta við | NumAfLausumSætum-- ef bókun er tekin frá, tengist greiðslu
|  | 2 | 20 | 13 | 13 |  | 15
9 | As a traveler with a fluctuating schedule, I wish to be able to cancel my reservation, so that if something unexpected were to arise, I can cancel the trip. | 1 | 20 | 13 | 13 |  | 15 |  | 1 | Bókun á ferð eyðist út | Tenging milli bókun og gagnagrunns sem heldur utan um pantanir | NumAfLausumSætum++ ef hætt er við bókun, tengist greiðslu
10 | As a pet owner I wish to be able to know if a trip I am planning to go on allows pets, so that I can take my friendly and obedient dog with me. | 1 | 3 | 3 | 2 |  | 3 | 2 | 5
11 | As a traveler with a limited time and a packed schedule, I wish to be able to see the estimated length of the trips before I decide to book one, so that I can choose a trip with a length suitable for me. | 1 | 1 | 5 | 3 |  | 3 | 2 | 3
12 | As a busy traveler I wish to be able to pay for the trips at the same time as I book them, so I can avoid having any money related issues right before the departure. | 1 | 5 | 8 | 8 |  | 8 |  | 2 | Möguleiki á að slá inn kreditkortanúmer | Valið um að borga núna, ef ekki þá tengist þetta fyrirfram pöntun - fær vissan tíma til að staðfesta pöntun og borga, ef ekki þá dettur pöntunin út
13 | As a handicapped person I wish to be able to see if the trips I wish to go on are suited and accessible to people like me before I book them, so I won't accidentally book something I am incapable of handling. | 1 | 3 | 3 | 2 |  | 3 | 2 | 4
14 | As an extreme traveler, I wish to be able to see the danger level of trips before booking them, so that I can be sure that I will get my desired amount of adrenaline on those trips. | 1 | 3 | 3 | 1 |  | 2 |  | 4,5
15 | As a traveler, I wish to be able to see detailed information about a trip before booking it, so that I can properly plan what I'll need to take with me and what to expect. | 1 | 5 | 2 | 5 |  | 5 | 3 | 2 | Birting á ítarlegum upplýsingum fyrir notendur | Texti um ferðir er birtur fyrir notendur til að sjá - er sýnilegur notendum áður en ferðir eru pantaðar
16 | As a traveler, I would want to know what trips offer hotel pickups, because I do not have a driver's license. | 1 | 5 | 5 | 2 |  | 5 | 2 | 3
17 | As a traveler staying in the Reykjavík area I want to know what trips are available in that part of the country, so I can stay close to the area. | 1 | 1 | 8 | 8 |  | 8 | 4 | 3
18 | As an employee who books day tours for a travel company I want to be able to see the options offered, so it will make my job easier. | 1 | 13 | 5 | 13 |  | 13 |  | 3
19 | As an elderly woman who's afraid of walking alone in the dark I want to know what day tours offer drop-offs to the hotels, so that I can feel safe and secure on my way home. | 1 | 5 | 8 | 3 |  | 6,5 | 2 | 3
20 | As a traveler I want to know how difficult and extreme the tours are rated before I choose my trips so I won't be disappointed. | 1 | 20 | 13 | 8 |  | 15 |  | 2.3 | Review system - stjörnugjöf | Notendur geta gefið stjörnur fyrir ferð, frá 1 - 5, það er vistað í gagnagrunni og tekið meðaltal af sem er birt á síðunni fyrir notendur til að sjá. Að auki er birt hversu margir hafa gefið stjörnur | Ef við höfum tíma - review system með texta
21 | As a traveler that likes extreme trips, I would like to know if health insurance is included in the package, so I'll know if I have to buy one myself or not. | 1 | 2 | 3 | 2 |  | 2 | 2 | 4
Note on H10: Berglind: já og nei valmöguleiki